## Planning Performance
SIZE ESTIMATION ACCURACy
| SIZE | Planned | Actual | Estimated | LPI | UPI | PROBE | Size Estimation Accuracy | Planned | Actual | Estimated
Assignment 2 | A&M | 251.97 | 179 |  |  |  | D | A 2 | 251.97 | 179
| Total | 251.97 | 179 | -- | -- | -- |  | A 3 | 78.41 | 62 | 110.37
Assignment 3 | A&M | 78.41 | 62 |  |  |  | C | A 4 | 165.91 | 92 | 227.44
| Total | 113.41 | 115 | 110.37 | -- | -- |  | A 5 | 102.31 | 138 | 152.48
Assignment 4 | A&M | 165.91 | 92 |  |  |  | C | A 6 | 63.06 | 83 | 38.25
| Total | 230.91 | 170 | 227.44 | -- | -- |  | A 7 | 90.14 | 142 | 88.89
Assignment 5 | A&M | 102.31 | 138 |  |  |  | C | Size Estimation Accuracy Erro
| Total | 118.31 | 150 | 152.48 | -- | -- |  | Program | %
Assignment 6 | A&M | 63.06 | 83 |  |  |  | B | A 2 | -29.96
| Total | 146.06 | 151 | 38.25 | 0 | 138.77 |  | A 3 | -29.93
Assignment 7 | A&M | 90.14 | 142 |  |  |  | A | A 4 | -44.55
| Total | 257.14 | 281 | 88.89 | 37.32 | 142.95 |  | A 5 | 34.88
[8 empty] | A 6 | 31.62
TIME ESTIMATION ACCURACy | [7 empty] | A 7 | 57.54 | 3.2667
|  | Planned | Actual | Estimated | LPI | UPI | PROBE | Time Estimation Accuracy Compact | Planned | Actual | Estimated
Assignment 2 | Time | 2000 | 1797 | 2000 | -- | -- | D | A 2 | 2000 | 1797 | 2000
[8 empty] | A 3 | 760 | 755 | 787.14
Assignment 3 | Time | 760 | 755 | 787.14 |  |  | C | A 4 | 1756.9 | 351 | 1756.86
[8 empty] | A 5 | 891.77 | 1387 | 891.77
Assignment 4 | Time | 1756.9 | 351 | 1756.86 |  |  | C | A 6 | 274.07 | 428 | 274.07
[8 empty] | A 7 | 875.37 | 748 | 875.37
Assignment 5 | Time | 891.77 | 1387 | 891.77 |  |  | C | Time Estimation Error
[8 empty] | Program | %
Assignment 6 | Time | 274.07 | 428 | 274.07 |  |  | C | A 2 | -10.15
[8 empty] | A 3 | -0.66
Assignment 7 |  | 875.37 | 748 | 875.37 | 287.12 | 1426.61 | B | A 4 | -80.05
[8 empty] | A 5 | 55.49
[8 empty] | A 6 | 56.06
[8 empty] | A 7 | -14.53
1.0267

## Quality Performance
DEFECT TYPES IN CODE AND DESIGN
|  | Design | Code |  |  |  | Frequency |  | % |  |  | Frequency | %
10 | Documentation | 0 | 0 |  | 80 | Function | 9 | 9 | 50 |  | Function | 9 | 50
20 | Syntax | 0 | 1 |  | 70 | Data | 6 | 15 | 33.3333 |  | Data | 6 | 83.3333
30 | Build, Package | 0 | 0 |  | 50 | Interface | 3 | 18 | 16.6667 |  | Interface | 3 | 100
40 | Assignment | 0 | 5 |  | 10 | Documentation | 0 | 18 | 0 |  | Documentation | 0 | 100
50 | Interface | 3 | 4 |  | 20 | Syntax | 0 | 18 | 0 |  | Syntax | 0 | 100
60 | Checking | 0 | 1 |  | 30 | Build, Package | 0 | 18 | 0 |  | Build, Package | 0 | 100
70 | Data | 6 | 0 |  | 40 | Assignment | 0 | 18 | 0 |  | Assignment | 0 | 100
80 | Function | 9 | 16 |  | 60 | Checking | 0 | 18 | 0 |  | Checking | 0 | 100
90 | System | 0 | 0 |  | 90 | System | 0 | 18 | 0 |  | System | 0 | 100
100 | Environment | 0 | 0 |  | 100 | Environment | 0 | 18 | 0 |  | Environment | 0 | 100
[6 empty] | Total | 18
Defect Density
| Design | Code
A2 | 27.93 | 67.04
A3 | 48.39 | 48.38
A4 | 10.87 | 21.74
A5 | 14.49 | 28.99
A6 | 24.1 | 12.05
A7 | 0 | 7.04
80 | Function | 16 | 16 | 59.2593
40 | Assignment | 5 | 21 | 77.7778
50 | Interface | 4 | 25 | 92.5926
20 | Syntax | 1 | 26 | 96.2963
60 | Checking | 1 | 27 | 100
10 | Documentation | 0 | 27 | 100
30 | Build, Package | 0 | 27 | 100
70 | Data | 0 | 27 | 100
90 | System | 0 | 27 | 100
100 | Environment | 0 | 27 | 100
| Total | 27
| Function | 16 | 59.2593
| Assignment | 5 | 77.7778
| Interface | 4 | 92.5926
| Syntax | 1 | 96.2963
| Checking | 1 | 100
| Documentation | 0 | 100
| Build, Package | 0 | 100
| Data | 0 | 100
| System | 0 | 100
| Environment | 0 | 100
DEFECTS REMOVED
| Design Review | Code Review | Test
A2 | 0 | 0 | 100.56
A3 | 32.26 | 48.39 | 16.13
A4 | 10.97 | 10.87 | 10.87
A5 | 14.5 | 28.99 | 7.25
A6 | 24.1 | 12.05 | 0
A7 | 0 | 7.04 | 0
Total Defects
A2 | 100.56
A3 | 96.77
A4 | 32.61
A5 | 50.73
A6 | 36.14
A7 | 7.04
53.975
[12 empty] | Total count | A&M Size
[11 empty] | A2 | 18 | 179 | 36
[11 empty] | A3 | 6 | 62 | 11
[11 empty] | A4 | 3 | 92
[11 empty] | A5 | 7 | 138 |  | 3.2727
[11 empty] | A6 | 3 | 83
[11 empty] | A7 | 1 | 142
INJECTED IN PHASE
[10 empty] | A3 | Defects | Plan | Actual
[11 empty] | Plan | 0 | 0
[11 empty] | DLD | 2.6 | 3
[11 empty] | DLDR | 0 | 0
[11 empty] | CODE | 4.2 | 3
[11 empty] | CR | 0 | 0
[11 empty] | Compile | 0.3 | 0
[11 empty] | UT | 0 | 0
[11 empty] | PM | 0 | 0
[11 empty] | Total | 7.1 | 6
[10 empty] | A4 | Defects | Plan | Actual
[11 empty] | Plan | 0 | 0
[11 empty] | DLD | 6.3 | 1
[11 empty] | DLDR | 0 | 0
| Defects per Size | Plan | Actual | [7 empty] | CODE | 9.1 | 2
| A3 | 7.1 | 6 | [7 empty] | CR | 0 | 0
| A4 | 15.9 | 3 | [7 empty] | Compile | 0.5 | 0
| A5 | 8.2 | 7 | [7 empty] | UT | 0 | 0
| A6 | 4.8 | 3 | [7 empty] | PM | 0 | 0
| A7 | 6.8 | 1 | [7 empty] | Total | 15.9 | 3
[10 empty] | A5 | Defects | Plan | Actual
[11 empty] | Plan | 0 | 0
[11 empty] | DLD | 3.2 | 0
[11 empty] | DLDR | 0 | 2
[11 empty] | CODE | 4.8 | 0
[11 empty] | CR | 0 | 4
[11 empty] | Compile | 0.2 | 0
[11 empty] | UT | 0 | 1
[11 empty] | PM | 0 | 0
[11 empty] | Total | 8.2 | 7
[10 empty] | A6 | Defects | Plan | Actual
[11 empty] | Plan | 0 | 0
[11 empty] | DLD | 1.8 | 2
[11 empty] | DLDR | 0 | 0
[11 empty] | CODE | 2.8 | 1
[11 empty] | CR | 0 | 0
[11 empty] | Compile | 0.1 | 0
[11 empty] | UT | 0.1 | 0
[11 empty] | PM | 0 | 0
[11 empty] | Total | 4.8 | 3
[10 empty] | A7 | Defects | Plan | Actual
|  | Defect Fix time | [8 empty] | Plan | 0 | 0
80 | Function | 1363 | [8 empty] | DLD | 2.7 | 0
50 | Interface | 305 | [8 empty] | DLDR | 0 | 0
70 | Data | 297 | [8 empty] | CODE | 3.9 | 1
40 | Assignment | 123 | [8 empty] | CR | 0 | 0
20 | Syntax | 20 | [8 empty] | Compile | 0.1 | 0
60 | Checking | 10 | [8 empty] | UT | 0.1 | 0
[11 empty] | PM | 0 | 0
[11 empty] | Total | 6.8 | 1

## Process Performance
Defect-removal rates and leverage vs unit tests
| Defects/h DLDR | Defects/h CR | Defects/h UT | DRL (DLDR/UT) | DRL (CR/UT)
A 3 | 3 | 2.1 | 2 | 1.5 | 1.1
A 4 | 1.6 | 1.3 | 1 | 1.5 | 1.3
A 5 | 0.9 | 0.9 | 0.7 | 1.3 | 1.3
A 6 | 0.8 | 2 | 0 | 0 | 0
A 7 | 0 | 1 | 0 | 0 | 0
| DRL (DLDR/UT) | DRL (CR/UT)
A 3 | 1.5 | 1.1
A 4 | 1.5 | 1.3
A 5 | 1.3 | 1.3
A 6 | 0.64865 | 1.6216
A 7 | 0 | 0.81081
2
1
0.7
[6 empty] | 3.7 | 1.2333
|  | DLDR Rate | Yield
|  | 93 | 66.67
|  | 144.38 | 100
|  | 64.39 | 100
|  | 34.87 | 100
|  | 61.49 | 0
CR Rate | Yield
43.76 | 75
112.99 | 50
32.57 | 100
168.81 | 100
136.75 | 100
A/FR | Yield
4.36 | 100
5.62 | 100
7.95 | 100
Review Rate | DLDR | CR | Both
A3 | 93 | 44 | 30
A4 | 144 | 123 | 66
A5 | 64 | 33 | 22
A6 | 35 | 169 | 29
A7 | 62 | 138 | 42
| 79.6 | 101.4 | 37.8

## Productivity
Program | Size Per Unit Hour
A2 | 5.98
A3 | 4.93
A4 | 15.75
A5 | 5.98
A6 | 11.65
A7 | 11.39